## Sheet1
SNO | PHASE | INPUT | ACTIVITY | RESPONSIBILITY | OUTCOME
1 | Test Planning | Project plan | Identify the Resosurces | Test Lead (70%) | Test Plan Document
| what to Test | Functional Requirments | Team Formation | Test Manager (30%)
| How to Test |  | Test Estimation
| When to Test |  | Preparation of Test Plan
Review on Test Plan
Test plan signoff
2 | Test Designing | Project plan | Preparing of Test scenarios | Test Lead (30%) | Test Cases Document
|  | Functional Requirments | Preparing of Test cases | Test Engineers (70%) | Tracability Matrix
|  | Test Plan Document | Reviews on Test cases
|  | Design Documents | Requirment Tracability Matrix
|  | Use cases | Test Case Sign-off
3 | Test Execution | Functional Requirments | Executing Test Cases | Test Lead (10%) | status/ Test Reports
|  | Test Plan Document | Preparing of Test Reports/logs | Test Engineers (90%)
|  | Test Cases Document | Identifying the defects
Build from development Team
4 | Defect/Bug Reporting & Tracking | Test Cases | Prepare the defect Report | Test Lead (10%) | Defect Report
|  | Test Reports/logs | Reporting Defects to developers | Test Engineers (90%)
5 | Test Closure | Test Reports | Analyzing the Test Reports | Test Lead/ Test Manager (70%) | Test Summary/closure Report
|  | Defect Reports | Analyzing the Bug Reporting | Test Engineers (30%) | Test Metrics
Evaluating exit criteria

## TestCases
Module Name | TestCase ID | TC Title | TC Description | pre-conditions | priority | Requirment ID | Steps/Actions | Expected Results | Actual Results | Test Data | Result
Login | TC1 | Verify the valid Login page |  | 1) Open the Chrome Browser 2) Enter the application url : https://www.gmail.com | p1 | Req ID 1 |  | Loginpage should navigate the home page |  |  | Pass

## RTM
Req No | Requirment Description | Tescasse ID's | Status
R1 | Login to the applkication | TC1,TC2, TC3 | TC1-passed TC2-Failed, TC3-passed
R2 | Serching the ticket | TC11,TC12,TC13